## Sheet1
Option | Scope | Committee | Problem Statement | Expected Duration | Benefits | Risks | PJM Recommended | IMM Recommended
2 | Limited - Reliability/Operation problem only; No market/pricing/compensation issues | Operating Committee | Existing OC Problem Statement | 5-6 months | Reliability issue addressed; Short timeline; Limited impact to stakeholders | Some market issues will not be addressed; Solution may not be a long term fix | Yes | No
3 | Phase A - Reliability problem; Phase B Market issues | Phase A - OC; Phase B - MRC direction (Sr. Task Force?) | Phase A - Existing OC Problem Statement; Phase B - Wider Scope problem statement (developed by IMM) | Phase 1: 5-6 months; Phase 2: 8-12 months | Reliability issue addressed; Allows issues to be worked in parallel | Possible large market impacts; Lengthy stakeholder process | No; but would support | No
3A | Phase A - Reliability problem; Phase B Market issues | MRC direction (Sr. Task Force?) | Wider Scope problem statement with Phase A and Phase B deliverables (to be developed) | Phase 1: 5-6 months; Phase 2: additional 8-12 months | Reliability issue addressed; Optimization and market fixes considered | Possible large market impacts; Lengthy stakeholder process; Issues worked in series | No; but would support | No
4 | Address issues with marginal benefit function definition and application within the current regulation market to address reliability/Operation/market issues | MRC direction (Sr. Task Force?) | Wider Scope problem statement (to be developed) | 12-18 months | Reliability issue addressed; More optimized regulation market; Same stakeholder group looking at all issues | Lengthy stakeholder process; Large impact | No | Yes