# PJM RTEP - 2021 State Agreement Approach (“SAA”) Proposal Window TO SUPPORT New Jersey offshore wind (“NJ OSW”)

# 2021 SAA Proposal Window TO SUPPORT NJ OSW: Option 1B

### Purpose of Proposal Window

PJM seeks technical solutions, also called proposals, to provide new onshore transmission facilities to connect at or near the point of landfall connection from the new offshore transmission facilities in responses to the problem statement Option 2 with the default or alternative onshore points of interconnection (POI).  Option 1b should only be used for proposals that require a new onshore substation to connect the offshore transmission facilities at or near landfall to the onshore transmission facilities.  If no new onshore substation is required, then Option 2 should be used to submit proposals for these onshore transmission facilities.

In addition to establishing an electrical connection between Option 2 transmission facilities and the selected POIs, these new onshore transmission facilities under Option 1b will include all tie-in work at the selected POIs and accommodate the tie-in work with the offshore transmission facilities that will be performed under Option 2.  These new onshore transmission facilities will be capable of supporting energy transfers, in the amounts specified by the proposers, from landfall connections to the selected POIs. Because these new transmission facilities will be considered PJM facilities, they will be subject to all applicable planning criteria (PJM, NERC, SERC, RFC, and Local Transmission Owner criteria) under the final set of technical solutions that are ultimately selected to support the New Jersey public policy requirements.

### Scope of Work

PJM is seeking proposals to support the buildout of up to 7,500 MW of offshore wind off the coast of New Jersey by 2035 per the NJBPU Order and the Proposal Window Overview document.

This Problem Statement is for Option 1b, which shall cover all necessary upgrade and/or greenfield solutions from default or alternative POIs up to and including the new onshore substations.  A complete proposal will focus on one default or alternative POI, any necessary substations to facilitate the transfer, and must be complete and responsive in fully addressing the transfer of offshore wind energy from any new onshore substations to the POI and include all tie-in work to POI substations. Unless otherwise specified, Option 1b proposals shall include capability to accommodate the default injection amounts in the Proposal Window Overview document. Proposers may submit separate Option 1b proposals to address different POIs or different solutions related to single POIs. Any interdependence issues or benefits relative to proposals for Options 1a, 2, 3, or other Option 1b proposals (for different POIs) should be clearly described in the proposal.

Proposed solutions should include the following:

  - A new onshore substation, which will be capable of interconnecting the offshore transmission facilities (Option 2) at landfall to a default or alternative POI. Scope should include:

    - Switching devices for the landfall transmission and submarine circuits from the offshore substation (Option 2) and transmission to a default or alternative POI.

    - Applicable AC power equipment such as transformers and reactive power compensation devices (e.g. reactors and/or STATCOMs, etc.) if voltage level transformation is required.

    - Applicable DC/AC inverters if required.

The onshore substation design shall include consideration of extreme weather conditions, such as hurricanes and flooding. Environmental and special local permit requirements shall be considered.

  - New HVAC or HVDC transmission lines from the new onshore substation to a default or alternative POI with minimum transfer capability consistent with the default injection amounts described in the Proposal Window Overview document, or alternative injection amounts proposed by the developer.

    - The circuit design, e.g. overhead transmission line (OHL), cable, or gas insulated line (GIL), shall be specified along with applicable route and structure designs.

  - Tie-in to the default or alternative POI

    - The design shall include any modification, including appropriate switching devices to accommodate the tie-in of the transmission lines from the new onshore substation to the default or alternative proposed POI, with the capability to accommodate default injection amounts described in the Proposal Window Overview document, or alternative proposed injection amounts.

    - Installation of inverter station and associated equipment if the transmission line from the onshore substation is DC.

    - Installation of new transformer(s) and associated equipment if the transmission line from the onshore substation is not the same voltage level as the proposed POI substation.

    - Specification of associated equipment as applicable and required, such as:

      - Cable to OHL transition structure if HVAC or HVDC cable is applied.

      - GIB or GIL structure if gas-insulated structure is applied.

      - Necessary relay and communication facilities and applicable ancillary facilities.

### Response Back To PJM (Deliverables)

This section describes the required elements of a complete proposal. The absence of any element renders the proposal incomplete and the proposal will not be considered for selection.

Often there are several viable solutions to a given violation. Include alternate solutions in separate proposals as described above. PJM will not accept proposals with multiple alternatives.

Five categories of information are described below; four are required for a complete package and one is conditional.

- Completed PJM Proposal Submittal Template (including project description, value proposition to NJ and cost control and risk mitigation measures)

- BPU Supplemental Offshore Wind Transmission Proposals Data Collection Form

- Technical analysis files and documentation

- Project diagrams and schedules

- Company evaluation and operations and maintenance information (if required)

#### PJM Proposal Submittal Template

The PJM Competitive Planner Tool is used for proposal(s) submittal and captures project details, such as the criteria violations or system constraints that are being targeted by the proposed solution, the overall and specific project descriptions and the details of cost commitment, if included. The Competitive Planner Tool and user guide are available on the Competitive Planning Process page: https://www.pjm.com/planning/competitive-planning-process.aspx.

All proposals will be made public and posted on pjm.com after the proposal window is closed. Mark all CEII and business confidential information for redaction from this public posting. Redact only information which meets the criteria of CEII or business proprietary and confidential information.

Redaction guidelines can be found in PJM Manual 14F, Section 6.2. Please note that this section provides guidance only. PJM reserves the right to challenge proposed redaction of information in order to ensure the appropriate level of transparency.

#### BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form

In addition to the PJM Competitive Planner Tool submittal template, proposers must fully complete and submit the BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form. This Data Collection Form will collect supplemental information related to proposals, including: a narrative description of the proposed project(s) and options; documentation of the projected benefits in terms of design, flexibility, ratepayer costs, and environmental impacts; an identification of major risks of (such as delay or non-completion risks, including the project-on-project risks created by the interdependence of the proposed project(s) and those of other transmission and offshore wind projects); strategies to limit risks to NJ customers; and cost recovery and containment provisions.

Proposing Entities shall include the following information in the BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form:

- Proposing Entity Name

- Company ID

- Project Title

- PJM Proposal ID

Proposers shall provide a completed BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form that includes confidential information and a redacted version which can be made public on PJM.com.  Redact only information which meets the criteria of CEII or business proprietary and confidential information.  Any information redacted in the BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form shall be subject to the redaction guideline requirements in PJM Manual 14F, Section 6.2.

#### Technical Analysis Files and Documentation

Include the following technical information to provide a complete project proposal package:

- If applicable, a detailed description of the operating modes and features of the proposed solution, and how such modes may be represented in PJM planning processes.

- An analysis report of the proposed solution which identifies the issues being addressed, the data and assumptions, the analysis conducted and alternatives considered.  Basic information can be included in the PJM Proposal Submittal Template.  Additional details can be submitted via the BPU Supplemental Data Collection Form.

- A detailed analysis spreadsheet showing the planning analysis results for the project.

- A set of updates to the power flow cases which model the proposed solution. Provide files in a format compatible with PSS/E version 34.7. Provide only solvable and convergent solutions. Include an idev, or equivalent type file in order to apply changes to other models. Assign a unique identifier when new busses are required. Provide contingencies in a single file for each contingency type. Organize the contingencies into one of three categories:

  - Modified Contingencies

  - New Contingencies

  - Deleted Contingencies

- A list of all proposed equipment including but not limited to transmission lines, cables, transformers, substations, reactive devices, HVDC converter stations, FACTS devices, breakers etc., along with the relevant equipment parameters and assumptions needed to examine all evaluation criteria.  Equipment parameters and assumptions include but are not limited to ratings, impedances, line lengths, limits, settings, operational recommendations and restrictions and other applicable parameters and assumptions.  This information should be supplied to support both steady-state and time domain analyses as applicable.

- Additional documentation required to verify the proposal.

#### Project Diagrams & Schedules

Provide project diagrams in the PJM Competitive Planner Tool to detail how the proposed solution will modify existing infrastructure, how new infrastructure will be configured and where new infrastructure will be sited. Project diagrams should include, but are not limited to, the following details:

- A system upgrade description, which shall provide the following details:

  - Each POI at existing substations should tie into a new onshore substation in response to this Problem Statement 1b. Specify the name, location and the corresponding POI of each new onshore substation(s).

  - System single line diagrams which layout each interconnection transmission line between the POI existing substations to the onshore substation(s). Specify the voltage level (kV), AC or DC, overhead line or underground cable or gas-insulated line (GIL), length and number of the circuits, etc.

  - Single line diagram of new onshore substations. Specify the voltage level, AC or DC, switching devices and all other applicable major equipment such as inverters, transformers, reactive power compensation/FACTS devices, control building, auxiliary power, etc.

  - Layout of each new onshore substation(s). Specify location, size and expansion capabilities.

  - Single line diagram of the transmission line tie-in plan at the POI existing substations. Specify the voltage level (kV), AC or DC, OHL or cable or GIL, switching devices, and all other applicable major equipment such as inverters, transformers, reactive power compensation/FACTS devices, control building, auxiliary power, etc.

  - Proposed route and ROW of the new T-lines, the new onshore substations, and the necessary expansion at the POI existing substations.

  - Conceptual plan for construction sequencing and major facility outages needed for construction, including reason (i.e. clearance, tie-in, equipment change-out, protection system changes), duration, and recallability.

  - An executive summary of constructability of the proposal, including but not limited to: (1) overall ROW and siting analysis (2) permit requirement and risk assessment; (3) schedule.

  - Confirmation of Pre-Submission Meeting with the New Jersey Department of Environmental Protection (NJ DEP) and summary of feedback from the Pre-Submission Meeting regarding the submitter’s project

- Substation general arrangement and station layout at the existing POI facilities and the new onshore Substation:

  - Area to be modified

  - Land ownership or acquisition plan, and applicable permits

  - Planned orientation of new circuit tie-ins, i.e. transmission lines from the onshore substation

  - Planned new additions and main equipment (switching devices, transformers, Reactors, Cap Banks, FACTS devices, inverters, if applicable)

  - Bus layouts (open air or GIB) and connections to the main equipment

  - Substation control building

  - Relay protection/communication/substation automation modifications

  - Additional station power ancillary facilities as needed

  - Special substation design consideration of the onshore substation due to environmental and local permit restrictions and resilience factors (for example, elevated foundations, indoor substation design, GIB/GIL, etc.)

  - Specific l design consideration of HVDC and FACTS devices connections, if proposed

  - Specific design consideration of OHL/GIB/GIL/Cable transition structure, if applicable

- Line routing diagram:

- Identify proposed route of the new transmission lines between POI existing substations and the onshore Substations

- Clearly identify where acquisition of right-of-way is required, and applicable major permits

- Specify voltage level (kV), AC or DC, overhead-line structures location, and underground cable conduit/duct, transition structure, and orientation of tie-in to the substations.

- Typical OH Transmission Line structure design

- Typical OH Transmission Line corridor cross sections

- Typical UG Cable duct bank cross-sections and manhole arrangement.

- Significant environmental or other encumbrances

- Provisions for harmonic mitigation equipment, which can include but not be limited to space for such equipment at onshore substation, as well as plan of harmonic study to assess existing harmonics and anticipated harmonics from OSW circuits and develop designs for appropriate mitigation equipment.

- Detailed project schedule. Include, at minimum, the following major work activities:

  - Engineering and design

  - Siting and permitting with risk assessments on permit approvals with regulatory agencies

  - ROW and land acquisition with risk assessment on business, residential and regulatory estates

  - Material procurement

  - Construction window, including major crossings of transmission lines, river, highway, train, bridge and other critical infrastructures

  - Other construction window restrictions including applicable environmental, wildlife animal protection and social restrictions along the proposed ROWs

  - Testing/commissioning and associated outages

#### Company Evaluation and Operations and Maintenance Information

For proposers seeking Designated Entity status, provide additional information which will aid PJM in understanding how the proposed solution will be developed, constructed, operated and maintained. Include this information in the PJM Competitive Planner Tool.

Relevant PJM Operating Agreement, Schedule 6, section 1.5.8(f).

Entity-Specific Criteria Considered in Determining the Designated Entity for a Project.  In determining whether the entity proposing a Short-term Project, Long-lead Project or Economic-based Enhancement or Expansion recommended for inclusion in the plan shall be the Designated Entity, the Office of the Interconnection shall consider:  (i) whether in its proposal, the entity indicated its intent to be the Designated Entity; (ii) whether the entity is pre-qualified to be a Designated Entity pursuant to Operating Agreement, Schedule 6, section 1.5.8(a); (iii) information provided either in the proposing entity’s submission  pursuant to the Operating Agreement, Schedule 6, section 1.5.8(a) or 1.5.8(c)(2) relative to the specific proposed project that demonstrates:  (1) the technical and engineering experience of the entity or its affiliate, partner, or parent company, including its previous record regarding construction, maintenance, and operation of transmission facilities relative to the project proposed; (2) ability of the entity or its affiliate, partner, or parent company to construct, maintain, and operate transmission facilities, as proposed, (3) capability of the entity to adhere to standardized construction, maintenance, and operating practices, including the capability for emergency response and restoration of damaged equipment; (4) experience of the entity in acquiring rights of way; (5) evidence of the ability of the entity, its affiliate, partner, or parent company to secure a financial commitment from an approved financial institution(s) agreeing to finance the construction, operation, and maintenance of the project, if it is accepted into the recommended plan; and (iv) any other factors that may be relevant to the proposed project, including but not limited to whether the proposal includes the entity’s previously designated project(s) included in the plan.

### Proposal Fees

All proposals, upgrade and greenfield solutions, with the exception of solutions submitted with an estimated cost of $5M or less, submitted for consideration in the 2021 SAA Proposal Window to Support NJ OSW are subject to an initial $5,000 deposit per the PJM Operating Agreement 1.5.8(c).

Relevant PJM Operating Agreement language in Section 1.5.8(c):

(c)(1)	All proposals submitted in the proposal windows must contain:  (i) the name and address of the proposing entity; (ii) a statement whether the entity intends to be the Designated Entity for the proposed project; (iii) the location of proposed project, including source and sink, if applicable; (iv) relevant engineering studies, and other relevant information as described in the PJM Manuals pertaining to the proposed project; (v) a proposed initial construction schedule including projected dates on which needed permits are required to be obtained in order to meet the required in-service date; (vi) cost estimates and analyses that provide sufficient detail for the Office of Interconnection to review and analyze the proposed cost of the project; and (vii) with the exception of project proposals submitted with cost estimates of $5 million or less, a $5,000 non-refundable deposit must be included with each project proposal submitted by a proposing entity that indicates an intention to be the Designated Entity.

(c)(1)(i)  In addition, any proposing entity indicating its intention to be the Designated Entity will be responsible for and must pay all actual costs incurred by the Transmission Provider to evaluate the submitted project proposal.  To the extent the Transmission Provider incurs costs to evaluate multiple submitted project proposals where such costs are not severable by individual project proposal, the Transmission Provider shall invoice equal shares of the non-severable costs among the project proposals that cause such non-severable costs to be incurred.  Notwithstanding this method of invoicing non-severable costs, non-severable costs will be jointly and severally owed by the proposing entities that cause such costs to be incurred.

(c)(1)(ii)  All non-refundable deposits will be credited towards the actual costs incurred by the Transmission Provider as a result of the evaluation of a submitted project proposal.

(c)(1)(iii)  Following the close of a proposal window but before the Transmission Provider incurs any third-party consultant work costs to evaluate a submitted project proposal, the Transmission Provider will issue to the proposing entity an initial invoice seeking payment of estimated costs to evaluate each submitted project proposal.  The estimated costs will be determined by considering the:  potential cost of consultant work, historical estimates for project proposals of similar scope, complexity and nature of the need, and/or technology and nature of the project proposal. The Transmission Provider may issue additional invoices to the proposing entity prior to the completion of the evaluation activities associated with a project proposal if the Transmission Provider receives updated actual cost information and/or upon consideration of the factors specified in this section.

(c)(1)(iv)  At the completion of the evaluation activities associated with a project proposal, the Transmission Provider will reconcile the actual costs with monies paid and, to the extent necessary, issue either a final invoice or refund.

(c)(1)(v)  The proposing party must pay any invoiced costs within fifteen (15) calendar days of the Transmission Provider sending the invoice to the proposing entity or its agent.  For good cause shown, this fifteen (15) calendar day time period may be extended by the Transmission Provider.  If the proposing entity fails to pay any invoice within the time period specified and/or extended by the Transmission Provider in accordance with this section, the proposing entity’s pre-qualification status may be suspended and the proposing entity will be ineligible to be a Designated Entity for any projects that do not yet have an executed Designated Entity Agreement.  Such a suspension and/or ineligibility will remain in place until the proposing entity pays in full all outstanding monies owed to the Transmission Provider as a result of the evaluation of the proposing entity’s project proposal(s).

The non-refundable deposit is due at the time of submission. Pay the non-refundable deposit by wire transfer to PJM Interconnection at:

| Wire transfer funds to: | PJM Interconnection, LLC |
| --- | --- |
| Bank Name: | PNC Bank, N.A. New Jersey |
| ABA Number: | 031207607 (Fed Wire and ACH) |
| Account Number: | 80-1358-9826 |
| Provide Reference*: | Order 1000 |

To ensure the non-refundable deposit is properly accounted for, include a reference to “Order 1000 – Competitive submittal PJM Id ###” in the subject, notes or addenda field of the wire transfer form.  Please note that the PJM ID ### will be displayed on the confirmation email you receive after submitting the proposal and is also identified on the competitive planner tool once a competitive proposal is initially saved.

The proposer also needs to provide the following information to PJM:

Company Info, Primary contact name, Billing email & Tax ID#.

The PJM Proposal ID can be located on the Existing Proposal screen in the PJM Competitive Planner Tool

### Timeline

4/15/2021: Opening of 2021 SAA Proposal Window to Support NJ OSW

8/13/2021: Close of 2021 SAA Proposal Window to Support NJ OSW at 11:59 p.m. Eastern Daylight

Notes:

- Confidentiality of individual proposals will be maintained for the duration of the window.

- Proposals received after close of the proposal window will not be accepted.

### Questions

Submit all questions about the proposal window to the PJM Planning Community. Submit questions involving confidential information or CEII under the “Confidential” topic on the Planning Community. Answers will be provided to all participants in the proposal window.

Please reference 2021 SAA Proposal Window to Support NJ OSW in all correspondence.

Notice

In accordance with the Open Access Transmission Tariff, Attachment M, the MMU has access to all data submitted to PJM through PJM’s competitive proposal window process.  See Manual 14F, section 8.4.4.

References

- Proposal Window Overview

### Document Revision History

4/15/2021 - V1 -      Original Problem Statement posted to the PJM Competitive Planning Process webpage: https://www.pjm.com/planning/competitive-planning-process.aspx.

5/26/2021 - V2 - 	Revision to incorporate additional details for proposal technical requirements

It is anticipated that most reliability criteria violations associated with interconnecting the NJ public policy resources to the POIs will be addressed through solutions for Option 1a.  Option 1b may cause or be subject to additional criteria violations and proposals must resolve these criteria violations as well.