# PJM RTEP - 2021 State Agreement Approach (“SAA”) Proposal Window TO SUPPORT New Jersey offshore wind (“NJ OSW”)

# 2021 SAA Proposal Window TO SUPPORT NJ OSW: Option 2

### Purpose of Proposal Window

PJM seeks technical solutions, also called proposals, to provide new offshore transmission facilities to transfer offshore wind energy from new offshore substations to onshore substations proposed in response to the Option 1b problem statement, or to a default or alternative POI where new onshore substations are not needed, in the injection amounts in the Proposal Window Overview document. Because these new transmission facilities will be considered PJM facilities, they will be subject to all applicable planning criteria (PJM, NERC, SERC, RFC, and Local Transmission Owner criteria) under the final set of technical solutions that are ultimately selected to support the New Jersey public policy requirements.

### Scope of Work

PJM is seeking proposals to support the buildout of up to 7,500 MW of offshore wind off the coast of New Jersey by 2035 per the NJBPU Order and the Proposal Window Overview document.

This Problem Statement is for Option 2, which shall cover a new offshore substation and all necessary greenfield solutions connecting the new offshore substation to an onshore substation either contemplated in response to the Option 1b problem statement, or to a default or alternative POI where onshore substations are not needed. A complete proposal will fully detail the connection between one proposed onshore substation (or a default or alternative POI), and new offshore substation(s) to collect offshore wind energy from one or more wind farms.  Proposals must be complete and responsive in fully addressing the transfer of offshore wind generation from any new offshore substation(s) to the proposed onshore substation (or a default or alternative POI), and include all tie-in work to that substation(s). Unless otherwise specified in the proposal, Option 2 proposals shall include capability to accommodate the default injection amounts in the Proposal Window Overview document. Proposers should submit separate Option 2 proposals to address different POIs or different solutions related to single POIs. Any interdependence issues or benefits relative to proposals for Options 1a, 1b, 3, or other Option 2 proposals (for different POIs) should be clearly described in the proposal.

Proposed solutions should include the following:

  - New offshore substation(s), which will interconnect with the new Option 1b proposed onshore substation or, a default or alternative POI where new onshore substations are not needed. Scope should include:

- Switching and control devices at landfall connection and submarine transmission from the offshore substation to the onshore substation(s), or a default or alternative POI.

- Substation facilities, switching devices, metering and control of interconnecting future offshore wind generation lead lines, with total minimum transfer capability described in the Proposal Window Overview document for the relevant POI, or alternative proposed injection amounts. A narrative description should be provided along with the conceptual drawings.

- Applicable AC power equipment such as reactive power compensation devices (e.g. reactors, condensers, STATCOMs, etc.), and transformer(s) if voltage level transformation is required.

- Applicable DC/AC Inverters if required.

- Necessary relay and communication facilities and applicable ancillary facilities.

- Necessary safety equipment and facilities at the offshore substation for Operation and Maintenance (O&M).

At minimum, provide plan of substation facilities, switching devices and control of interconnecting future offshore grid circuit which will connect the offshore substations, if applicable (Option 3).

- Installation method, floating or fixed installed, of the offshore substation platform should be specified.

The offshore substation design shall include consideration of extreme weather conditions including hurricanes. Environmental and special offshore infrastructure permit requirements shall be considered.

  - New HVAC or HVDC landfall connection and submarine transmission from the new offshore substation(s) to the onshore substation(s), a default or alternative POI, with a minimum transfer capability as described in the Proposal Window Overview document for the relevant POI, or alternative proposed injection amounts.

- The circuit design, e.g. submarine cable, or gas insulated line (GIL), shall be specified along with applicable route and structure designs, ROW cross sections, and manhole arrangements, as applicable.

- Installation method for submarine cables and crossing of landfall interfaces.

- Environmental and special local permit requirements shall be considered.

  - Tie-in to Option 1b proposed onshore substation, default POI or alternative POI.

- The design shall include any modification, including appropriate switching devices, to the proposed onshore substation, default POI, or alternative POI, to accommodate the tie-in of the transmission line from the offshore substation, with the capability to accommodate the injections specified in the Proposal Window Overview document, or alternate proposed injection amounts.

- Installation of inverter station and associated equipment if the offshore transmission line to the onshore substation is DC.

- Installation new transformer(s) and associated equipment if the transmission line from the onshore substation requires voltage transformation.

- Specification of associated equipment as applicable and required, such as:

  - Cable to OHL transition structure if HVAC or HVDC cable is applied.

  - GIB or GIL structure if gas-insulated structure is applied.

  - Necessary relay and communication facilities and applicable ancillary facilities.

### Response Back To PJM (Deliverables)

This section describes the required elements of a complete proposal. The absence of any element renders the proposal incomplete and the proposal will not be considered for selection.

Often there are several viable solutions to a given violation. Include alternate solutions in separate proposals as described above. PJM will not accept proposals with multiple alternatives.

Five categories of information are described below; four are required for a complete package and one is conditional.

- Completed PJM Proposal Submittal Template (including project description, value proposition to NJ and cost control and risk mitigation measures)

- BPU Supplemental Offshore Wind Transmission Proposals Data Collection Form

- Technical analysis files and documentation

- Project diagrams and schedules

- Company evaluation and operations and maintenance information (if required)

#### PJM Proposal Submittal Template

The PJM Competitive Planner Tool is used for proposal(s) submittal and captures project details, such as the criteria violations or system constraints that are being targeted by the proposed solution, the overall and specific project descriptions and the details of cost commitment, if included. The Competitive Planner Tool and user guide are available on the Competitive Planning Process page: https://www.pjm.com/planning/competitive-planning-process.aspx.

All proposals will be made public and posted on pjm.com after the proposal window is closed. Mark all CEII and business confidential information for redaction from this public posting. Redact only information which meets the criteria of CEII or business proprietary and confidential information.

Redaction guidelines can be found in PJM Manual 14F, Section 6.2. Please note that this section provides guidance only. PJM reserves the right to challenge proposed redaction of information in order to ensure the appropriate level of transparency.

#### BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form

In addition to the PJM Competitive Planner Tool submittal template, proposers must fully complete and submit the BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form. This Data Collection Form will collect supplemental information related to proposals, including: a narrative description of the proposed project(s) and options; documentation of the projected benefits in terms of design, flexibility, ratepayer costs, and environmental impacts; an identification of major risks of (such as delay or non-completion risks, including the project-on-project risks created by the interdependence of the proposed project(s) and those of other transmission and offshore wind projects); strategies to limit risks to NJ customers; and cost recovery and containment provisions.

Proposing Entities shall include the following information in the BPU Supplemental Offshore Wind Transmission Proposal data Collection Form:

- Proposing Entity Name

- Company ID

- Project Title

- PJM Proposal ID

#### Proposers shall provide a completed BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form that includes confidential information and a redacted version which can be made public on PJM.com.  Redact only information which meets the criteria of CEII or business proprietary and confidential information.  Any information redacted in the BPU Supplemental Offshore Wind Transmission Proposal Data Collection Form shall be subject to the redaction guideline requirements in PJM Manual 14F, Section 6.2.

#### Technical Analysis Files and Documentation

Include the following technical information to provide a complete project proposal package:

- If applicable, a detailed description of the operating modes and features of the proposed solution, and how such modes may be represented in PJM planning processes.

- An analysis report of the proposed solution which identifies the issues being addressed, the data and assumptions, the analysis conducted and alternatives considered.  Basic information can be included in the PJM Proposal Submittal Template.  Additional details can be submitted via the BPU Supplemental Data Collection Form.

- A detailed analysis spreadsheet showing the planning analysis results for the project.

- A set of updates to the power flow cases which model the proposed solution. Provide files in a format compatible with PSS/E version 34.7. Provide only solvable and convergent solutions. Include an idev, or equivalent type file in order to apply changes to other models. Assign a unique identifier when new busses are required. Provide contingencies in a single file for each contingency type. Organize the contingencies into one of three categories:

  - Modified Contingencies

  - New Contingencies

  - Deleted Contingencies

- A list of all proposed equipment including but not limited to transmission lines, cables, transformers, substations, reactive devices, HVDC converter stations, FACTS devices, breakers etc., along with the relevant equipment parameters and assumptions needed to examine all evaluation criteria.  Equipment parameters and assumptions include but are not limited to ratings, impedances, line lengths, limits, settings, operational recommendations and restrictions and other applicable parameters and assumptions.  This information should be supplied to support both steady-state and time domain analyses as applicable.

- Additional documentation required to verify the proposal.

#### Project Diagrams and Schedules

Provide project diagrams in the PJM Competitive Planner Tool to detail how the proposed solution will modify existing infrastructure, how new infrastructure will be configured and where new infrastructure will be sited. Project diagrams should include, but are not limited to, the following details:

- A system upgrade description, which shall provide the following details:

  - Specify the name, location and layout of each new offshore substation(s).

  - System single line diagrams which illustrate the layout of each interconnecting transmission line between the offshore substation(s) and the new Option 1b onshore substation(s) or default or alternative POIs. Specify the voltage level (kV), AC or DC, submarine cable, overhead line or underground cable or gas-insulated line (GIL) for landfall connection, length and number of the circuits, etc.

  - Voltage rating, number of circuit positions, and total offshore wind capacity receipt.

  - Voltage rating, number of circuit positions, and total Option 3 capacity receipt/delivery.

  - Proposed high-voltage submarine cable design including type and size of conductor, type of insulation and expected ampacity.

  - Proposed submarine cable system corridor from each new offshore substation to each landfall location.  Specify the number of submarine cables which will reside within each corridor and the minimum separation between each submarine cable.

  - Characterize the water depths along the submarine cable system corridors and the subsea soil geotechnical and thermal conditions including any known environmental or physical encumbrances.

  - Describe the submarine cable installation technique and the target burial depths.

  - Describe the scope of future submarine cable corridor surveys required to finalize the submarine cable system design, installation methods, and environmental permit applications.

  - Provide the location for each proposed submarine cable corridor landfall and the required ROW necessary to install the specified number of submarine cables.

  - Provide a description of the submarine cable to land cable or land transmission transition.

  - Provide a description on how the submarine cable will be installed at each landfall location (e.g., directional drill).

  - Proposed route and ROW of the new T-lines from each landfall location to the new Option 1b onshore substations or default or alternative POIs.

  - Single line diagram of the transmission line tie-in plan at the onshore substations. Specify the voltage level (kV), AC or DC, OHL or cable or GIL, switching devices, and all other applicable major equipment such as inverters, transformers, reactive power compensation/FACTS devices, control building, auxiliary power, etc.

  - Layout of each new offshore substations. Specify size and expansion capabilities.

  - Facility access plan and methods for construction, equipment installation, and maintenance activities.

  - Plan for offshore materials/parts storage, maintenance and shop facilities, and crew facilities.

  - Water depth at each offshore substation location.

  - Single line diagram of new offshore substations. Specify the voltage level, AC or DC, switching devices and all other applicable major equipment such as inverters, transformers, reactive power compensation/FACTS devices, control building, auxiliary power, etc.

  - Plan for supplying facility auxiliary power during outages and energization of transmission cable(s) back to the mainland.

  - A detailed description of the offshore collector substation features shall be provided along with the conceptual drawings for OSW generation lead-line tie-in and future offshore grid line tie-ins.

  - Conceptual plan for construction sequencing and major facility outages of existing facilities as applicable, including reason (i.e. clearance, tie-in, equipment change-out, protection system changes), duration, and recallability.

  - Plan and location of equipment and materials staging and transport methods to offshore locations.

  - An executive summary of constructability of the proposal, including but not limited to: (1) overall ROW and siting analysis (2) Permit requirement and risk assessment; (3) schedule.

  - Confirmation of Pre-Submission Meeting with the New Jersey Department of Environmental Protection (NJ DEP) and summary of feedback from the Pre-Submission Meeting regarding the submitter’s project

- Substation general arrangement and station layout at the new Option 1b onshore substation, or default or alternative POI if Option 1b is not required:

  - Area to be modified at the existing default or alternative POI facilities, if applicable

  - Connections to the new Option 1b onshore substations, if applicable

  - Land ownership or acquisition plan, and applicable permits

  - Planned orientation of new circuit tie-ins, i.e. transmission lines from the offshore  substation

  - Planned new additions and main equipment (switching devices, transformers, reactors, cap banks, FACTS devices, Inverters, if applicable)

  - Bus layouts (open air or GIB) and connections to the main equipment

  - Substation control building

  - Relay protection/communication/substation automation modifications

  - Additional station power ancillary facilities as needed

  - Special substation design consideration of the offshore substation due to environmental and local permit restrictions, necessary facilities and design considerations for safety, operational & maintenance, and extreme weather factors (for example, elevated foundations, indoor substation design, GIB/GIL, etc.)

  - Specific design consideration of HVDC and FACTS devices connections, if proposed

  - Specific design consideration of OHL/GIB/GIL/cable transition structure, if applicable

- Line routing diagram:

- Identify proposed route of the new transmission lines between the offshore substations and Option 1b new onshore substation, default POIs at existing substations or alternative POIs

- Clearly identify where acquisition of right-of-way is required, and applicable major permits

- Specify voltage level (kV), AC or DC, overhead-line structures location and underground cable conduit/duct for landfall connection, submarine cable installation route, transition structure (if applicable), connections between offshore substation modules (if applicable), and orientation of tie-in to the substations.

- Provisions for harmonic mitigation equipment, which can include but not be limited to space for such equipment at offshore substation, as well as plan of harmonic study to assess existing harmonics and anticipated harmonics from OSW circuits and develop designs for appropriate mitigation equipment.

- Detailed project schedule. Include, at minimum, the following major work activities:

  - Engineering and design

  - Siting and permitting with risk assessments on permit approvals with regulatory agencies

  - ROW and land acquisition with risk assessment on business, residential and regulatory estates

  - Material procurement

  - Construction window, including major crossings of transmission lines, river, highway, train, bridge and other critical infrastructures

  - Other construction window restrictions including applicable environmental, wildlife animal protection and social restrictions along the proposed ROWs

  - Testing/commissioning and associated outages

#### Company Evaluation and Operations and Maintenance Information

For proposers seeking Designated Entity status, provide additional information which will aid PJM in understanding how the proposed solution will be developed, constructed, operated and maintained. Include this information in the PJM Competitive Planner Tool.

Relevant PJM Operating Agreement, Schedule 6, section 1.5.8(f).

Entity-Specific Criteria Considered in Determining the Designated Entity for a Project.  In determining whether the entity proposing a Short-term Project, Long-lead Project or Economic-based Enhancement or Expansion recommended for inclusion in the plan shall be the Designated Entity, the Office of the Interconnection shall consider:  (i) whether in its proposal, the entity indicated its intent to be the Designated Entity; (ii) whether the entity is pre-qualified to be a Designated Entity pursuant to Operating Agreement, Schedule 6, section 1.5.8(a); (iii) information provided either in the proposing entity’s submission  pursuant to the Operating Agreement, Schedule 6, section 1.5.8(a) or 1.5.8(c)(2) relative to the specific proposed project that demonstrates:  (1) the technical and engineering experience of the entity or its affiliate, partner, or parent company, including its previous record regarding construction, maintenance, and operation of transmission facilities relative to the project proposed; (2) ability of the entity or its affiliate, partner, or parent company to construct, maintain, and operate transmission facilities, as proposed, (3) capability of the entity to adhere to standardized construction, maintenance, and operating practices, including the capability for emergency response and restoration of damaged equipment; (4) experience of the entity in acquiring rights of way; (5) evidence of the ability of the entity, its affiliate, partner, or parent company to secure a financial commitment from an approved financial institution(s) agreeing to finance the construction, operation, and maintenance of the project, if it is accepted into the recommended plan; and (iv) any other factors that may be relevant to the proposed project, including but not limited to whether the proposal includes the entity’s previously designated project(s) included in the plan.

#### Transmittal of Proposals

Proposal submissions along with all files required for submission will be done with the PJM Competitive Planner Tool for each submitted proposal.

### Proposal Fees

All proposals, upgrade and greenfield solutions, with the exception of solutions submitted with an estimated cost of $5M or less, submitted for consideration in the 2021 SAA Proposal Window to Support NJ OSW are subject to an initial $5,000 deposit per the PJM Operating Agreement 1.5.8(c).

Relevant PJM Operating Agreement language in Section 1.5.8(c):

(c)(1)	All proposals submitted in the proposal windows must contain:  (i) the name and address of the proposing entity; (ii) a statement whether the entity intends to be the Designated Entity for the proposed project; (iii) the location of proposed project, including source and sink, if applicable; (iv) relevant engineering studies, and other relevant information as described in the PJM Manuals pertaining to the proposed project; (v) a proposed initial construction schedule including projected dates on which needed permits are required to be obtained in order to meet the required in-service date; (vi) cost estimates and analyses that provide sufficient detail for the Office of Interconnection to review and analyze the proposed cost of the project; and (vii) with the exception of project proposals submitted with cost estimates of $5 million or less, a $5,000 non-refundable deposit must be included with each project proposal submitted by a proposing entity that indicates an intention to be the Designated Entity.

(c)(1)(i)  In addition, any proposing entity indicating its intention to be the Designated Entity will be responsible for and must pay all actual costs incurred by the Transmission Provider to evaluate the submitted project proposal.  To the extent the Transmission Provider incurs costs to evaluate multiple submitted project proposals where such costs are not severable by individual project proposal, the Transmission Provider shall invoice equal shares of the non-severable costs among the project proposals that cause such non-severable costs to be incurred.  Notwithstanding this method of invoicing non-severable costs, non-severable costs will be jointly and severally owed by the proposing entities that cause such costs to be incurred.

(c)(1)(ii)  All non-refundable deposits will be credited towards the actual costs incurred by the Transmission Provider as a result of the evaluation of a submitted project proposal.

(c)(1)(iii)  Following the close of a proposal window but before the Transmission Provider incurs any third-party consultant work costs to evaluate a submitted project proposal, the Transmission Provider will issue to the proposing entity an initial invoice seeking payment of estimated costs to evaluate each submitted project proposal.  The estimated costs will be determined by considering the:  potential cost of consultant work, historical estimates for project proposals of similar scope, complexity and nature of the need, and/or technology and nature of the project proposal. The Transmission Provider may issue additional invoices to the proposing entity prior to the completion of the evaluation activities associated with a project proposal if the Transmission Provider receives updated actual cost information and/or upon consideration of the factors specified in this section.

(c)(1)(iv)  At the completion of the evaluation activities associated with a project proposal, the Transmission Provider will reconcile the actual costs with monies paid and, to the extent necessary, issue either a final invoice or refund.

(c)(1)(v)  The proposing party must pay any invoiced costs within fifteen (15) calendar days of the Transmission Provider sending the invoice to the proposing entity or its agent.  For good cause shown, this fifteen (15) calendar day time period may be extended by the Transmission Provider.  If the proposing entity fails to pay any invoice within the time period specified and/or extended by the Transmission Provider in accordance with this section, the proposing entity’s pre-qualification status may be suspended and the proposing entity will be ineligible to be a Designated Entity for any projects that do not yet have an executed Designated Entity Agreement.  Such a suspension and/or ineligibility will remain in place until the proposing entity pays in full all outstanding monies owed to the Transmission Provider as a result of the evaluation of the proposing entity’s project proposal(s).

The non-refundable deposit is due at the time of submission. Pay the non-refundable deposit by wire transfer to PJM Interconnection at:

| Wire transfer funds to: | PJM Interconnection, LLC |
| --- | --- |
| Bank Name: | PNC Bank, N.A. New Jersey |
| ABA Number: | 031207607 (Fed Wire and ACH) |
| Account Number: | 80-1358-9826 |
| Provide Reference*: | Order 1000 |

To ensure the non-refundable deposit is properly accounted for, include a reference to “Order 1000 – Competitive submittal PJM Id ###” in the subject, notes or addenda field of the wire transfer form.  Please note that the PJM ID ### will be displayed on the confirmation email you receive after submitting the proposal and is also identified on the competitive planner tool once a competitive proposal is initially saved.

The proposer also needs to provide the following information to PJM:

Company Info, Primary contact name, Billing email & Tax ID#.

The PJM Proposal ID can be located on the Existing Proposal screen in the PJM Competitive Planner Tool

### Timeline

4/15/2021: Opening of 2021 SAA Proposal Window to Support NJ OSW

8/13/2021: Close of 2021 SAA Proposal Window to Support NJ OSW at 11:59 p.m. Eastern Daylight

Notes:

- Confidentiality of individual proposals will be maintained for the duration of the window.

- Proposals received after close of the proposal window will not be accepted.

### Questions

Submit all questions about the proposal window to the PJM Planning Community. Submit questions involving confidential information or CEII under the “Confidential” topic on the Planning Community. Answers will be provided to all participants in the proposal window.

Please reference 2021 SAA Proposal Window to Support NJ OSW in all correspondence.

Notice

In accordance with the Open Access Transmission Tariff, Attachment M, the MMU has access to all data submitted to PJM through PJM’s competitive proposal window process.  See Manual 14F, section 8.4.4.

References

- Proposal Window Overview

### Document Revision History

4/15/2021 - V1 -      Original Problem Statement posted to the PJM Competitive Planning Process webpage: https://www.pjm.com/planning/competitive-planning-process.aspx.

5/26/2021 - V2 - 	Revision to incorporate additional details for proposal technical requirements

It is anticipated that most reliability criteria violations associated with interconnecting the NJ public policy resources to the POIs will be addressed through solutions for Option 1a.  Option 2 may cause or be subject to additional criteria violations and proposals must resolve these criteria violations as well.